## Slide 1: Chapter 3: An overview of project planning
Part 1
NET481: Project Management

## Slide 2: Topics to be covered
Project Planning in an organized step by step manner
Different techniques and how they are fit into an overall planning approach
The need to repeat the planning process in more details for some activities within a project before execution

## Slide 3: Planning Activities‭ ‬Steps
Step 0‭: ‬Select project‭
Step 1‭: ‬Identify project scope and objectives
Step 2‭: ‬Identify project infrastructure
Step 3‭: ‬Analyze project characteristics‭
Step 4‭: ‬Identify project products and activities‭
Step 5‭: ‬Estimate effort for each activity‭

## Slide 4: Planning Activities‭ ‬Steps (cont.)
Step 6‭: ‬Identify activity risks‭
Step 7‭: ‬Allocate resources‭
Step 8‭: ‬Review/publicize plan‭
Step 9‭: ‬Execute plan
Step 10‭: ‬Execute lower levels of planning‭

## Slide 5: An overview of step wise

## Slide 6: Step 0: Select Project
This is called step 0 because in a way it is outside the main project planning process.

## Slide 7: Step 1: ‬Identify Project Scope and‭ Objectives
    Step 1.1‭ ‬Identify objectives and practical measures of the‭
effectiveness in meeting those objectives‭.
Correct definition of objectives‭.
Identify measures of effectiveness for your objectives‭.
Measures of effectiveness provides practical methods‭ of checking that an
object has been met.
Ex‭: ‬measuring reliability‭:
      Mean time between failures‭. (‬Performance measure‭)
      Number of errors found during code inspections‭.‬ (‬Predictive measure‭)

## Slide 8: Step 1‭ (cont.)
Step 1.2‭ ‬Establish a project authority‭.
  To ensure the unity of purpose among all persons concerned‭.
  The project authority is usually‭:
    A project steering committee
    ‬A project board or project management board‭
  The project authority have overall responsibility for setting‭,
  monitoring and modifying objectives‭.
  The project manager runs the project but reports regularly to the
  steering committee‭

## Slide 9: Step 1‭ (cont.)
Step 1.3‭ ‬Identify all stakeholders in the project and their interests.‭
Step 1.4‭ ‬Modify objectives in the light of stakeholder analysis
  Based on the stakeholders requirements‭, ‬it might be necessary to modify the
  project objectives‭.
  ‬ E.g.‭. ‬Adding new features to the system‭.
  This has to be done in a controlled manner‭.

## Slide 10: Step 1‭ (cont.)
Step 1.5‭ ‬Establish methods of communication between all‭ parties
  Communication between stakeholders is important in all kinds of projects
  It is more important to arrange for in a dispersed project‭.
  the way stakeholders will communicate is part of the‭ project planning

## Slide 11: Step 1‭ (cont.)
There has to be a communication plan‭:
  List the main stakeholders‭.
  With special attention to those involved in the‭
  development and implementation‭.
  List their concerns‭.
  Identify suitable methods for effective communication
  consulting stakeholder’s representatives would be a‭ help

## Slide 12: Step 1‭ (cont.)
The communication plan could be documented in a table
with‭ the following headings:
  What‭? ‬ Name of the meeting‭.
  Who‭? Target audience‭.
  Purpose‭. ‬
  When/frequency‭?
  Type/method‭?
    E.g‭. ‬Meeting or a document distribution‭.
  Responsibility‭.
    the person initiating the meeting‭.

## Slide 13: Step 2: Identify Project Infrastructure
Step 2.1‭ ‬Identify relationship between the project and strategic
Planning
Select the projects to be carried out by an organization‭. ‬
Project portfolio
Programme management‭.
  managing a group of projects together in a coordinated way
  It can ensure that a group of projects contribute to a common
  organizational strategy

## Slide 14: Step 2‭ (cont.)
Establish a framework within which the system fits‭.
  hardware and software standards should be followed‭.
  The software or components to be created should be
  compatible with those created by previous projects and with
  the existing HW and SW platforms‭.

## Slide 15: Step 2‭ (cont.)
Step 2.2‭ ‬Identify installation standards and procedures‭.
  Identify standards and procedures related to the software
  project
    E.g‭. ‬specifying quality checks needed at each point of the project
    Life cycle
  The project manager should be aware of the Project planning
  and control standards‭.
    E.g how are hours spent by team members on tasks recorded on‭ ‬
    timesheets.

## Slide 16: Step 2‭ (cont.)
Step 2.3‭ ‬Identify project team organization‭.
  e.g‭. ‬a high level manager could decide that‭:
  software developers and business analysts could be in‭ different
  group

## Slide 17: Step 3‭: ‬Analyse Project Characteristics
Step 3.1‭ ‬Distinguish the project as either objective-driven or
product-driven‭.
Step 3.2‭ ‬Analyse other project characteristics‭ (‬including‭
  quality-based ones‭).
  Step 3.3‭ ‬Identify high level project risks‭. ‬

## Slide 18: Step 3‭ (cont.)
Step 3.4‭ ‬Take into account user requirements concerning‭
implementation‭.
  E.g‭. ‬an organization might mandate the use of a particular
  method.
  Step 3.5‭ ‬Select general life-cycle approach in the light of the
  above‭.

## Slide 19: Step 3‭ (cont.)
Step 3.6‭ ‬Review overall resource estimates‭.
Up to this stage‭:
  the major risks of the project are identified‭
  the overall approach of the project is decided
  So‭, ‬it is a good place to re-estimate the required effort and
  other resources for the project‭