## Slide 1: Chapter 7: Risk Management
Project Management
Afnan Albahli

## Slide 2: Risk Definition
Definition of Risk:
‘an uncertain event or condition that, if it occurs has a positive or negative effect on a project’s objectives’.
‘the chance of exposure to the adverse consequences of future events’.

## Slide 3: Risk Key Elements
• It relates to the future.
– The future is uncertain.
– Some things that seem obvious when the project is over, might not have appeared obvious during planning (e.g. technology used, project estimation).
• It involves a cause and an effect.
– Causes:
  • The use of untrained staff.
  • Poor specifications.
  • An inaccurate estimate of effort.
– Effects:
  • Cost over run.
  • Low productivity.

## Slide 4: Exercise
Match the risk cause to the risk effect(s).
Causes:
  Staff inexperience.
Effects:
  I. Testing takes longer than planned.
  II. Planned effort and time for activities exceeded.
  III. Project scope increases.
  IV. Time delays in getting changes to plans agreed.

## Slide 5: Boundaries of Risk Management
● Every plan is based on assumptions and risk
management tries to plan for and control the situations where those assumptions become incorrect.
● Risk planning is carried out at steps: 3 & 6.

## Slide 6: Risk Categories
• Project Risks: are risks that could prevent the achievement of the objectives given to the project manager and the project team.
• These objectives are formulated toward achieving project success.
• Project success factors:
  – On time.
  – Within budget.
  – Required functionality.
  – Quality.
• Project risks can be classified under these four categories.

## Slide 7: Risk Categories (cont’d)
A different way to categorize risks:
• A sociotechnical model proposed by Kalle Lyytinen and his colleagues

## Slide 9: Risk Categories (cont’d)
• Actors : refers to all people involved in the development of the application.
• Risk:
  • A high staff turnover, leads to expertise of value to the project being lost.
• Technology: encompasses both the technology:
  – Used to implement the application and
  – That embedded in the delivered products.
• Risk:
  – Relating to the appropriateness of the technology and
  – The possible faults in it.

## Slide 10: Risk Categories (cont’d)
• Structure: describes the management structures and systems, including those affecting planning and control.
• Risk:
• Responsibility for managing the users involvement at the implementation stage might not be clearly allocated.
• Tasks: relates to the work planned.
• Risk:
• The complexity of work might lead to delays because of
the additional time required integrate the large number
of components.

## Slide 11: Risk Framework
Planning for risk includes these steps:
  1. Risk identification.
  2. Risk analysis and prioritization.
  3. Risk planning.
  4. Risk monitoring.
• When risks are identified, plans can be made to reduce or remove their effects.
• The plans are reassessed to ensure:
  – That the original risks are reduced sufficiently and
  – No new risks are inadvertently introduced.

## Slide 12: Risk Identification
The two main approaches to identify risk are:
  – The use of checklists.
  – Brainstorming.
Checklists: are lists of the risks that have been found to occur regularly in software development projects.
• Those checklists often suggest some potential countermeasures for each risk.
• A group of representatives for a project examines a checklist identifying risks applicable to their project.
• PRINCE2, recommends that after completing a project, all the problems that were identified as risks during the project to be added to an organizational risk checklist to be used with new projects.

## Slide 13: Software Project Risk Checklist Example

## Slide 14: Risk Identification (cont’d)
Brainstorming (thinking ahead):
Representatives of the main stakeholders of the project, are brought together , in order to use their individual knowledge of different parts of the project
➔ to identify the problems that can occur (identify risks).

## Slide 15: Risk Assessment (Risk analysis and prioritization)
In order to prioritize the risks that were identified, we need a way to distinguish:
  • The likely and damaging risks from those identified in the previous step “risk identification”.
One way of doing so is to calculate the risk exposure for each risk identified, using the following formula:
Risk Exposure (RE)= (potential damage) ×(probability of occurrence)

## Slide 16: Risk Assessment (cont’d)
Ways of assessing the potential damage and probability of occurrence:
1. In money values and probabilities.
  Say a project depended on a data center vulnerable to fire. It might be estimated that if fire occurred a new computer configuration could be established for $500,000. it might also be estimated that there is a 1 in 1000 chance that a fire will occur.
The risk exposure (RE) in this case would be:
500,000 *0.001=$500
*The higher the RE, the more attention or priority is given to
the risk

## Slide 17
With some risks:
Instead of damages, there could be gains.
Example:
a task that is scheduled to take six days is completed in 3 days instead.
A project leader may produce a probability chart for the tasks.

## Slide 18: Probability chart

## Slide 19: Probability chart
● The probability completion: shows the probability of completing the task in x days.
● The accumulated probability: shows the probability of completing the task on or before the xth day.

## Slide 20: Risk Assessment (cont’d)
2. Relative scales from 0 to 10.
• Both risk loss (damage) and the likelihood (probability of occurrence) will be assessed using relative scales from 0 to 10.
• Then they will be multiplied together to get a notional risk exposure (RE).

## Slide 21: Risk Exposure (RE)
Risk in the table refers to the Risk Exposure (RE)

## Slide 22: Risk Planning
• After:
– The major risks are identified and
– Prioritized.
• The task becomes “how to deal with them”.
• The choices for dealing with them are:
– Risk acceptance.
– Risk avoidance.
– Risk reduction and mitigation.
– Risk transfer.

## Slide 23: Risk Planning (cont’d)
• Risk Acceptance:
– This is deciding to do nothing about the risk. This means you will accept its consequences. Why?
– In order to concentrate on the more likely or damaging risks.
– The damage that those risks could cause would be less than the costs needed to act towards reducing their probability of occurrence.

## Slide 24: Risk Planning (cont’d)
• Risk Avoidance:
– Some activities are so prone to accident that it is best to avoid them altogether.
– Example to avoid all the problems associated with developing software solutions from scratch, a solution could be to:
• Buy an off-the-shelf product.

## Slide 25: Risk Planning (cont’d)
• Risk Reduction and Mitigation:
– Risk Reduction: attempts to reduce the likelihood of the risk occurring.
e.g. consider the following risk: developers leaving a
company in the middle of a project for a better paid job.
In order to reduce the probability of such a risk occurring:
the developers could be promised to be paid generous
bonuses on successful completion of the project.

## Slide 26: Risk Planning (cont’d)
– Risk Mitigation: is the action taken to ensure that the impact of the risk is reduced when it occurs.
Taking regular backups of data storage, is it a risk mitigation measure or a risk reduction measure?
Since it would reduce the impact of data corruption not its likelihood of happening, in this sense it is a data mitigation measure.

## Slide 27: Risk Planning (cont’d)
Risk Transfer:
– In this case the risk is transferred to another person or organization.
– Example: a software development task is outsourced for a fixed fee.
– Another example is when you buy insurance( e.g. for a car).

## Slide 28: Risk Management
Contingency Plans:
• Although risk reduction measures try to reduce the probability or the likelihood of risks, they still could happen.
• Contingency plan is a planned action to be carried out if a risk materializes (occurs).

## Slide 29: Risk Management (cont’d)
Creating and maintaining the risk register:
• A risk register: it contains the findings of project planners of what appear to be the most threatening risks to the project.
• After work starts on a project more risks will appear and will be added to the register.
• Risk registers are reviewed and updated regularly.