Project Management

Assignment 2 - due on Wed 7/ 6/1434

(1 Problem)

Consider the following table of information:

| Activity | Duration (Weeks) | Precedence |
| --- | --- | --- |
| A | 2 | - |
| B | 10 | A |
| C | 2 | A |
| D | 2 | A |
| E | 3 | B |
| F | 2 | C, D |
| G | 4 | E, F |

- Draw the precedence network by performing the forward and backward passes.(Activity on Node)

- Determine the critical path and completion date of the project.

- Draw the Critical Path by performing the forward and backward passes.(Activity on Arrow)