NET481

Tutorial #6 – chapter  7+8

Q1: Below are details of a project. All times are in days

| Activity | Depends on | Most likely | Plus safety |
| --- | --- | --- | --- |
| A |  | 10 | 14 |
| B | A | 5 | 7 |
| C | B | 15 | 21 |
| D | A | 3 | 5 |
| E | A | 8 | 12 |
| F | E | 20 | 22 |
| G | D | 6 | 8 |
| H | C,F,G | 10 | 14 |

- Using (i) the most likely and then (ii) the safety estimates

- Calculate the earliest and latest start and end days and float for each activity;

- Identify the critical path

ES = Earliest start EF = Earliest finish LS = Latest start LF = Latest finish

The critical path (with all floats zero) is…………………………….

Based on most likely durations

| Activity | Depends on | Most likely | ES | Duration | EF | LS | LF | Float |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A |  | 10 | 0 | 10 | 10 | 0 | 10 | 0 |
| B | A | 5 | 10 | 5 | 15 | 18 | 23 | 8 |
| C | B | 15 | 15 | 15 | 30 | 23 | 38 | 8 |
| D | A | 3 | 10 | 3 | 13 | 29 | 32 | 19 |
| E | A | 8 | 10 | 8 | 18 | 10 | 18 | 0 |
| F | E | 20 | 18 | 20 | 38 | 18 | 38 | 0 |
| G | D | 6 | 13 | 6 | 19 | 32 | 38 | 19 |
| H | C,F,G | 10 | 38 | 10 | 48 | 38 | 48 | 0 |

Based on durations with a safety factor

| Activity | Depends on | Plus safety | ES | duration | EF | LS | LF | float |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A |  | 14 | 0 | 14 | 14 | 0 | 14 | 0 |
| B | A | 7 | 14 | 7 | 21 | 20 | 27 | 6 |
| C | B | 21 | 21 | 21 | 42 | 27 | 48 | 6 |
| D | A | 5 | 14 | 5 | 19 | 35 | 40 | 21 |
| E | A | 12 | 14 | 12 | 26 | 14 | 26 | 0 |
| F | E | 22 | 26 | 22 | 48 | 26 | 48 | 0 |
| G | D | 8 | 19 | 8 | 27 | 40 | 48 | 21 |
| H | C,F,G | 14 | 48 | 14 | 62 | 48 | 62 | 0 |

Q2: Mo is a systems analyst who is gathering requirements for an application which will record details of the training undertaken by fire-fighters in the client fire brigade. Details of the training units successfully completed by fire-fighters are to be input to the application by trainers who are themselves senior and active fire-fighters. Mo needs to interview a trainer to obtain his/her requirements. Because of the senior fire-fighters’ other duties the interview has to be arranged two weeks in advance. There is then a 20% chance of the fire-fighter being unable to attend the interview because of an emergency call-out. Each week that the project is delayed costs the fire brigade approximately £1000.

  - Provide an estimate of the risk exposure (as a financial value) for the risk that the senior fire-fighter might not be able to attend at the times needed.

The risk exposure is therefore 20% of £2000, that is £400.

  - Suggest possible risk mitigation actions.

Given the risk exposure of £400, there would be a case of paying someone overtime to cover for the firefighter/trainer who is being interviewed.

Alternatively, appointments could be made with two trainers at different times within the same week. This would not completely eliminate the risk, as it is possible for emergencies to happen at the times of both arranged interviews.

Q3: 5	 (a) Draw up an activity network and calculate the earliest finish for the following project:

| activity | duration | depends on | resource type |
| --- | --- | --- | --- |
| A | 3 days |  | SA |
| B | 1 day | A | SD |
| C | 2 days | B | SD |
| D | 4 days | A | SD |
| E | 3 days | A | SC |
| F | 3 days | E | SC |
| G | 6 days | D | SC |
| H | 3 days | C,F,G | SA |

SA = Systems analyst; SD = Systems designer; SC = Software coder

| Activity | ES | duration | EF | LF | LS | float |
| --- | --- | --- | --- | --- | --- | --- |
| A | 0 | 3 | 3 | 3 | 0 | 0 |
| B | 3 | 1 | 4 | 10 | 9 | 6 |
| C | 4 | 2 | 6 | 10 | 8 | 5 |
| D | 3 | 4 | 7 | 7 | 3 | 0 |
| E | 3 | 3 | 6 | 13 | 10 | 6 |
| F | 6 | 3 | 9 | 13 | 10 | 5 |
| G | 7 | 6 | 13 | 13 | 7 | 0 |
| H | 13 | 3 | 16 | 16 | 13 | 0 |

The critical path  is…A,D,G,H……………….

(b) Produce a table showing the number of specialists of each type needed on each day of the project. How many of each type of resource will need to be recruited for the project as a whole if the earliest finish date is to be preserved?

| Weeks | 1-3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14-16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SA1 | A |  |  |  |  |  |  |  |  |  |  |  |
| SA2 |  |  |  |  |  |  |  |  |  |  |  | H |
| SD1 |  | B |  |  |  |  |  |  |  |  |  |  |
| SD2 |  |  | C | C |  |  |  |  |  |  |  |  |
| SD3 |  | D | D | D | D |  |  |  |  |  |  |  |
| SC1 |  | E | E | E |  |  |  |  |  |  |  |  |
| SC2 |  |  |  |  | F | F | F |  |  |  |  |  |
| SC3 |  |  |  |  |  | G | G | G | G | G | G |  |
| SAs | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| SDs |  | 2 | 2 | 2 | 1 |  |  |  |  |  |  |  |
| SCs |  | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 |  |

(c) What impact would there be on the project if there were only two systems coder?

| Weeks | 1-3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14-16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SA1 | A |  |  |  |  |  |  |  |  |  |  |  |
| SA2 |  |  |  |  |  |  |  |  |  |  |  | A |
| SD1 |  | B |  |  |  |  |  |  |  |  |  |  |
| SD2 |  |  | C | C |  |  |  |  |  |  |  |  |
| SD3 |  | D | D | D | D |  |  |  |  |  |  |  |
| SC1 |  | E | E | E | F | F | F |  |  |  |  |  |
| SC2 |  |  |  |  |  | G | G | G | G | G | G |  |
| SAs | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| SDs |  | 2 | 2 | 2 | 1 |  |  |  |  |  |  |  |
| SCs |  | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  |

No impact if there are only 2 system coders.