NET481

Tutorial #5 – chapter 5 + 6

Q1:

Given the project data below:

| project | inputs | outputs | entity accesses | system users | program-ming language | developer days |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 210 | 420 | 40 | 10 | x | 30 |
| 2 | 469 | 1406 | 125 | 20 | x | 85 |
| 3 | 513 | 1283 | 76 | 18 | y | 108 |
| 4 | 660 | 2310 | 88 | 200 | y | 161 |
| 5 | 183 | 367 | 35 | 10 | z | 22 |
| 6 | 244 | 975 | 65 | 25 | z | 42 |
| 7 | 1600 | 3200 | 237 | 25 | y | 308 |
| 8 | 582 | 874 | 111 | 5 | z | 62 |
| X | 180 | 350 | 40 | 20 | y |  |
| Y | 484 | 1190 | 69 | 35 | y |  |

Note X and Y are new projects for which estimates of effort are needed.

What would be the estimated effort for projects X and Y using a Mark II function point count?

| project | inputs | outputs | entity accesses | system users | program-ming language | developer days | FPs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 210 | 420 | 40 | 10 | x | 30 |  |
| 2 | 469 | 1406 | 125 | 20 | x | 85 |  |
|  |  |  |  | sub-totals |  |  |  |
|  |  |  |  | productivity (FPs/day) |  |  |  |
| 3 | 513 | 1283 | 76 | 18 | y | 108 |  |
| 4 | 660 | 2310 | 88 | 200 | y | 161 |  |
| 7 | 1600 | 3200 | 237 | 25 | y | 308 |  |
|  |  |  |  | sub-totals |  | 577 |  |
|  |  |  |  | productivity (FPs/day) |  |  |  |
| 5 | 183 | 367 | 35 | 10 | z | 22 |  |
| 6 | 244 | 975 | 65 | 25 | z | 42 |  |
| 8 | 582 | 874 | 111 | 5 | z | 62 |  |
|  |  |  |  | sub-totals |  | 126 |  |
|  |  |  |  | productivity (FPs/day) |  |  |  |
| X | 180 | 350 | 40 | 20 | y |  |  |
| Y | 484 | 1190 | 69 | 35 | y |  |  |

Q2:

Q3: Create a precedence activity network using the following details:

Calculate the earliest and latest start and end dates and the float associated with each activity.

From this identify the critical path.

| Activity | Depends on | Duration (days) |
| --- | --- | --- |
| A |  | 5 |
| B | A | 7 |
| C | B | 6 |
| D | A | 5 |
| E | D | 10 |
| F | B | 15 |
| G | B | 8 |
| H | G | 8 |
| I | C | 4 |
| J | G | 4 |
| K | E,F | 5 |
| L | I,H | 3 |

Q4:take another look at brigette's collage payroll activity network fragment , which related to the earlier software selection procces and which you developed in tutorial#3 .Redrow this as an activity-on-arrow network .